Project Plan

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

04/29/25

The Let It Snow MT project focuses on creating a real-time snow reporting website for Montana’s ski resorts. Developed by Broken Unlimited LLC, the platform will address the need for centralized snow and weather information, offering features like interactive maps, customizable filters, and administrative tools. Accurate and timely data will be integrated through APIs, ensuring users have access to up-to-date snow conditions, temperatures, and resort updates.

Built with the average Montana skier in mind, the website will cater to those people looking for reliable information while promoting tourism across Montana. By increasing resort attendance and streamlining snow reporting, the project aims to benefit both users and stakeholders. Using an agile approach, the development follows structured phases; design, integration, testing, and launch, to ensure the timely delivery of a polished product by August 2025.

Let It Snow MT is more than a tool—it’s a gateway to enhanced winter recreation, empowering resorts and communities while driving tourism and economic growth.

Table of Contents

- Business Case

- p. 4-8

- Project Proposal

- p. 9-12

- Project Charter

- p. 13-17

- Project Brief

- p. 18-21

- Scope Statement

- p. 22-26

- Team Charter

- p. 27-30

- Project Schedule and Work Breakdown

- p. 31-36

- Requirements Gathering

- p. 37-41

- Project Budget

- p. 42-44

- Project Communication Plan

- p. 45-48

- Risk Register
p. 49-51

Business Case

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

01/12/25

TABLE OF CONTENTS

- EXECUTIVE SUMMARY
1.1. Issue
1.2. Anticipated Outcomes
1.3. Recommendation
1.4. Justification

- BUSINESS CASE ANALYSIS TEAM

- PROBLEM DEFINITION
3.1. Problem Statement
3.2. Organizational Impact
3.3. Technology Migration

- PROJECT OVERVIEW
4.1. Project Description
4.2. Goals and Objectives
4.3. Project Performance
4.4. Project Assumptions
4.5. Project Constraints
4.6. Major Project Milestones

- STRATEGIC ALIGNMENT

- COST BENEFIT ANALYSIS

- ALTERNATIVES ANALYSIS

- APPROVALS

EXECUTIVE SUMMARY

1.1. Issue:
Skiers, snowboarders, and resort operators in Montana lack a centralized platform for accessing up-to-date snow reports and resort conditions. Users often rely on fragmented and unreliable data sources.

1.2. Anticipated Outcomes:
By implementing the Let It Snow MT website, users will benefit from real-time snow conditions and resort updates in one platform. The solution is expected to enhance user satisfaction, increase resort attendance, and boost Montana’s tourism economy during winter seasons.

1.3. Recommendation:
Develop an interactive, user-friendly website with integrated APIs to provide accurate snow and weather data. Features include a real-time interactive map, customizable filters, mobile compatibility, and administrative tools for site management. Agile development practices will ensure iterative improvements based on stakeholder feedback.

1.4. Justification:
The website supports Montana’s ski resorts by consolidating critical snow and weather data into one platform. It will improve user experiences, drive tourism revenue, and provide insights into customer behavior. Without this project, Montana risks continued fragmentation of snow reporting and missed opportunities for economic growth and incredible days of skiing.

BUSINESS CASE ANALYSIS TEAM

- Project Sponsor: Scott Flinders

- Project Manager: Cameron Flinders

- Development Team: Cameron Flinders

- Stakeholders: Montana ski resorts, tourism boards, and outdoor enthusiasts

PROBLEM DEFINITION

3.1. Problem Statement:
The absence of a unified snow reporting system leaves users searching multiple sources for reliable information. This inefficiency frustrates users and hinders the ability of ski resorts to maximize attendance.

3.2. Organizational Impact:
The website will streamline operational processes for resort operators by centralizing snow reporting and data updates. It will also enhance communication with users, improve decision-making based on real-time insights, and help enthusiasts better enjoy skiing in Montana.

3.3. Technology Migration:
The project will integrate third-party APIs for snow and weather data, ensuring real-time updates. Existing data processes at resorts should feed seamlessly for easy integration by state resorts.

PROJECT OVERVIEW

4.1. Project Description:
This project involves the development and implementation of an interactive snow reporting website for Montana ski resorts. The site will provide real-time data, filters for customization, and an interactive map. Agile development practices will be used throughout its lifecycle.

4.2. Goals and Objectives:

- Deliver accurate, real-time snow and weather reports

- Provide a user-friendly, mobile-compatible interface

- Promote Montana tourism through improved resort engagement

4.3. Project Performance:
Performance will be gauged through metrics such as user engagement, accuracy of snow data, and overall site traffic.

4.4. Project Assumptions:

- Reliable integration with third-party APIs

- Users will adopt the new system over fragmented sources

- Stakeholders will provide timely feedback

4.5. Project Constraints:

- API reliability and integration

- Limited availability of development resources

- Deadline tied to the start of the ski season

4.6. Major Project Milestones:

- Requirements finalization

- Initial design

- Development of core features

- User testing and feedback implementation

- Website deployment

STRATEGIC ALIGNMENT
The Let It Snow MT project aligns with Montana’s strategic plans to enhance tourism and economic growth in the winter sports sector. The project supports these goals by offering a centralized resource for snow reporting and resort updates, making better user experience.

COST BENEFIT ANALYSIS
The total project cost is estimated at $68,000, including labor, API integrations, hosting, and miscellaneous expenses. Project benefits include increased tourism revenue, reduced information gaps, and user engagement through interactivity, which are expected to exceed project costs within the first ski season.

ALTERNATIVES ANALYSIS
Alternatives considered:

- Status Quo: Continue using fragmented snow reporting systems. This option fails to address user frustrations or promote tourism effectively.

- Third-Party Solutions: Use an existing snow report service, but these lack customization and ski/snowboard specific focus.
The recommended approach is to develop a bespoke, interactive website tailored to Montana’s needs.

Project Proposal

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

02/01/25

1. Executive Summary
The Let It Snow MT project proposes the development of an interactive, real-time snow reporting website tailored to Montana’s ski resorts. The website will consolidate snow conditions, temperatures, and resort updates into a single user-friendly platform, addressing the lack of centralized snow information. This project aims to improve user satisfaction, increase resort attendance, and promote tourism across Montana. The proposed solution includes innovative features like an interactive map, customizable filters, and administrative tools, with a scalable and mobile-compatible design.

2. Project Objectives

- Provide a centralized platform for real-time snow and weather updates for Montana ski resorts.

- Improve user experiences with an intuitive, mobile- compatible interface.

- Promote tourism by increasing awareness and attendance at Montana ski resorts.

3. Project Scope
The project includes:

- Design and Development: Create a website with integrated APIs for real-time snow data.

- Interactive Features: Include a map, filtering options, and mobile compatibility.

- Administrative Tools: Provide site administrators with analytics and monitoring capabilities.

- Testing and Training: Perform system testing and deliver user training materials.

The project excludes long-term hosting, data updates beyond initial integrations, and post-launch efforts.

4. Key Deliverables

- Fully functional and responsive snow reporting website.

- API integrations for accurate, real-time snow and weather data.

- User documentation for site management and troubleshooting.

- Testing reports demonstrating system performance and reliability.

### 5.Project Milestones

| Milestone | Target Completion Date |
| --- | --- |
| Requirements Gathering and Finalization | 04/15/25 |
| Initial Design Prototypes | 05/01/25 |
| Development and Feature Integration | 06/15/25 |
| User Testing and Feedback Implementation | 07/15/25 |
| Website Launch | 08/01/25 |

### 6. Budget Overview

| Expense Category | Estimated Cost |
| --- | --- |
| Internal Labor | $50,000 |
| API Costs | $10,000 |
| Web Hosting | $5,000 |
| Miscellaneous | $3,000 |
| Total | $68,000 |

7. Proposed Approach
An agile development methodology will be used, with iterative sprints to incorporate stakeholder feedback. Best practices in web development will ensure scalability, security, and user-friendly design. The project team will conduct regular reviews and testing to maintain alignment with stakeholder goals.

8. Benefits and Justification
The Let It Snow MT website will bridge the gap in centralized snow reporting, providing significant benefits:

- Enhanced User Experience: Outdoor enthusiasts will have easy access to reliable and up-to-date information.

- Tourism Growth: Increased engagement and resort attendance will support Montana’s economy.

- Operational Insights: Resorts will benefit from analytics and improved data integration.

Without this project, the lack of a centralized platform will continue to hinder Montana’s winter tourism potential and user satisfaction.

9. Risk Assessment

- API Dependency: The project relies on the availability and accuracy of third-party APIs for data.

- Time Constraints: Strict deadlines tied to the ski season may impact timelines.

- Resource Availability: Limited availability of development team member.

Mitigation strategies include early API testing, detailed project planning, and efficient resource allocation.

10. Conclusion
The Let It Snow MT project offers a practical, innovative solution to address the challenges of fragmented snow reporting in Montana. Its successful implementation will enhance the experience of outdoor enthusiasts, promote tourism, and contribute to the state’s economic growth. Stakeholder support and investment in this project will ensure timely delivery and long-term value creation.

Project Charter Plan

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

02/17/25

TABLE OF CONTENTS

- EXECUTIVE SUMMARY

- PROJECT PURPOSE/JUSTIFICATION

  - Business Need/Case

  - Business Objectives

- PROJECT DESCRIPTION

  - Project Objectives and Success Criteria

  - Requirements

  - Constraints

  - Assumptions

  - Preliminary Scope Statement

- RISKS

- PROJECT DELIVERABLES

- SUMMARY MILESTONE SCHEDULE

- SUMMARY BUDGET

- PROJECT APPROVAL REQUIREMENTS

- PROJECT MANAGER

- AUTHORIZATION

EXECUTIVE SUMMARY

Montana's numerous ski resorts currently lack a centralized platform for real-time snow reporting and resort conditions. This gap causes skiers and snowboarders to rely on scattered and inconsistent information sources. The Let It Snow MT Website Project has been created to address this issue by developing an interactive website that displays up-to-date snow data across the state for relevant ski resorts. The website will provide users with a seamless, user-friendly experience, while promoting Montana’s winter sports tourism.

PROJECT PURPOSE/JUSTIFICATION

Business Need/Case

The project addresses the organizational need to enhance Montana's reputation as a skiing destination by providing a centralized, accurate, and engaging platform for snow reporting. The interactive website will support the state’s tourism goals, attract more visitors, and provide a modern digital tool for ski resort operators and enthusiasts to find up-to-date and accurate data.

Business Objectives

This project directly supports strategic tourism goals by:

- Designing and launching a user-friendly, interactive snow reporting website by the start of the next ski season.

- Promoting Montana ski resorts, boosting visitor attendance by 20% in the first year.

- Enhancing skier satisfaction and streamlining access to snow condition information.

PROJECT DESCRIPTION

Project Objectives and Success Criteria

- Develop and test a feature-rich, interactive snow report website within 120 days.

- Integrate accurate snow and weather data via APIs and ensure seamless functionality.

- Achieve a 95% user satisfaction rate based on post-launch surveys.

- Deliver the project on time and within budget constraints.

Requirements

- Real-time snow condition updates for all ski resorts in Montana.

- A responsive, mobile-compatible design with an intuitive user interface.

- Data filters (e.g., snowfall, resort, and temperature).

- Administrative dashboard for managing website content and monitoring analytics.

Constraints

- Data integration must rely on external APIs/data for snow reporting.

- The project must be completed within four months to meet the ski season deadline.

Assumptions

- Resort operators will collaborate by providing required data and testing.

- The project sponsor will ensure budget approval without delays.

- No significant delays will occur in securing API access or integrating third-party data sources.

Preliminary Scope Statement

This project includes the design, development, testing, and deployment of a fully functional interactive website for snow reports. It will integrate reliable data sources, feature an intuitive interface for users, and support Montana ski resorts by promoting tourism. Ongoing maintenance and marketing activities post-launch are outside the scope of this project.

RISKS

- Delays in securing API access or integrating third-party data.

- Low user adoption if website functionality or design fails to meet expectations.

- Budget overruns due to unforeseen development challenges.

PROJECT DELIVERABLES

- Fully functional website with real-time snow data.

- Integration with weather and snow condition APIs or third-party data.

- Mobile-compatible platform.

- Administrative documentation and user training materials.

SUMMARY MILESTONE SCHEDULE

| Project Milestone | Target Date (mm/dd/yyyy) |
| --- | --- |
| Project Start | 01/01/2025 |
| Complete Requirements Gathering | 02/15/2025 |
| Prototype and UI Design Completed | 05/01/2025 |
| Complete API Integration | 07/15/2025 |
| Testing and Debugging Completed | 08/15/2025 |
| Website Launch | 09/01/2025 |

SUMMARY BUDGET

| Project Component | Component Cost |
| --- | --- |
| Personnel Resources | $50,000 |
| API Integration | $10,000 |
| Website Hosting and Maintenance | $5,000 |
| Design and Development Tools | $7,000 |
| Marketing/Promotional Budget | $8,000 |
| Total | $80,000 |

PROJECT APPROVAL REQUIREMENTS

The project will be considered successful if it:

- Delivers a fully functional and user-friendly website by the start of the ski season.

- Achieves stakeholder satisfaction, including ski resort operators and end-users.

- Stays within budget and meets all defined requirements.

PROJECT MANAGER

Cameron Flinders is designated as the Project Manager for the Let It Snow MT Website Project. The Project Manager will oversee all activities, communicate project progress, and ensure timely resolution of issues. The Project Manager will report directly to the project sponsor.

AUTHORIZATION

By signing below, the Project Sponsor authorizes the project to proceed in accordance with the details outlined in this charter.

Project Sponsor: Scott Flinders Title: Investor Date: 02/01/25

Project Brief

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

03/01/25

Let It Snow MT – Montana Snow Reporting Website
The Let It Snow MT project proposes the development of an interactive website to provide real-time snow reporting for all ski resorts in Montana. This platform addresses the unconsolidated availability of reliable snow condition data, enabling users to access consolidated information in a user-friendly interface. Its purpose is to enhance the planning experience for skiers and snowboarders, promote tourism, and support Montana’s winter sports economy.

Goals and Objectives

- Goals:

  - Deliver accurate, real-time snow and weather updates for Montana ski resorts.

  - Improve user satisfaction through an intuitive, mobile-compatible design.

  - Encourage increased attendance at Montana ski resorts, boosting local tourism.

- SMART Objectives:

  - Develop and launch the website by August 1, 2025, prior to the ski season.

  - Achieve at least 95% user satisfaction based on post-launch surveys.

  - Ensure 100% API uptime for reliable snow and weather data during the ski season.

Project Scope

- Included:

  - Website design and development.

  - Integration with third-party APIs for real-time snow and weather data.

  - Testing phases to ensure quality and functionality.

  - Creation of user training materials and documentation.

- Excluded:

  - Ongoing website maintenance or hosting post-launch.

  - Marketing and promotion activities.

  - Updates to third-party data beyond initial API integration.

Key Deliverables

- Fully functional and responsive snow reporting website.

- An interactive map for ease of use.

- Data filtering and customization options for users.

- API integration or integrating third-party data for real-time data accuracy.

- User training materials and a testing report to verify system performance.

Project Timeline

| Phase | Target Date |
| --- | --- |
| Requirements Gathering | April 15, 2025 |
| Initial Design Prototypes | May 1, 2025 |
| Development of Core Features | June 15, 2025 |
| User Testing and Feedback | July 15, 2025 |
| Website Launch | August 1, 2025 |

Stakeholders

- Primary Stakeholders: Montana ski resorts and operators, skiers, and snowboarders.

- Project Sponsor: Broken Unlimited LLC.

- Project Team:

  - Project Manager: Oversees planning, progress, and stakeholder communication.

  - Development Team: Responsible for design, coding, and integration tasks.

Budgets and Resources

- Budget Overview:

  - Internal Labor: $50,000

  - API Costs: $10,000

  - Web Hosting: $5,000

  - Miscellaneous: $3,000

  - Total Estimated Cost: $68,000

- Resources Needed:

  - Development tools and software for website creation.

  - Access to third-party APIs for snow and weather data.

  - Testing devices for both desktop and mobile platforms.

Constraints

- Dependence on reliable third-party APIs for snow data.

- Limited availability of development resources due to concurrent projects.

- A strict timeline to ensure the website is ready for the 2025 ski season.

Success Criteria

- A responsive website launched by August 1, 2025 without critical errors.

- Real-time data accuracy meeting user expectations as verified in testing.

- Achieving at least 95% user satisfaction in feedback surveys post-launch.

- Regular site traffic throughout ski season

Project Scope

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

03/17/25

TABLE OF CONTENTS

- INTRODUCTION

- PROJECT PURPOSE AND JUSTIFICATION

- SCOPE DESCRIPTION

- HIGH-LEVEL REQUIREMENTS

- BOUNDARIES

- STRATEGY

- DELIVERABLES

- ACCEPTANCE CRITERIA

- CONSTRAINTS

- COST ESTIMATE

- COST BENEFIT ANALYSIS

INTRODUCTION

This Project Scope Statement outlines the scope, deliverables, and work required to successfully develop and implement an interactive website that displays real-time snow reports and conditions for all ski resorts in Montana. This document aims to ensure a shared understanding of the project’s objectives among stakeholders and provides a outline for guiding all project activities.

PROJECT PURPOSE AND JUSTIFICATION

The Montana Snow Report Website Project has been initiated to provide skiers, snowboarders, and resort operators with a central, interactive platform for accessing up-to-date snow reports and resort conditions. Montana boasts numerous ski resorts, but the lack of a unified reporting system often leaves users searching multiple sources for reliable information. This project aims to fill that gap, offering a user-friendly website that consolidates data while enhancing the experience for outdoor enthusiasts.

The website will not only drive traffic from skiing and snowboarding enthusiasts but also promote tourism across Montana. By providing accurate and real-time data, it is expected to improve user satisfaction, increase resort attendance, and contribute to the state's growing winter sports economy.

SCOPE DESCRIPTION

The scope of this project includes the design, development, testing, and deployment of an interactive snow reporting website for Montana ski resorts. The website will feature:

- Real-time updates on snow conditions, temperatures, and resort statuses.

- An interactive map for a user-friendly way to see snow conditions across resorts.

- Filters for users to customize the information displayed (e.g., resort name, snowfall in the last 24 hours).

- Integration with APIs to pull weather and snow condition data.

- User-friendly design optimized for both desktop and mobile devices.

- Analytics dashboard for site administrators to monitor site performance and user activity.

This project includes all requirements gathering, design, coding, system integration, testing, and user training. Ongoing site maintenance is outside the project's scope.

HIGH-LEVEL REQUIREMENTS

- Interactive map displaying real-time snow conditions across Montana ski resorts.

- API integration with reliable sources for snow, weather, and resort data.

- Desktop and mobile-compatible user interface.

- Data filtering and customization options for users.

- Secure data storage and privacy-compliant infrastructure.

- Administrative tools for monitoring and managing the website.

BOUNDARIES

The project includes:

- Development of a fully functional website with snow reporting capabilities.

- Integration with weather and snow condition APIs.

- Initial user training and documentation for site maintenance.

The project excludes:

- Long-term maintenance or hosting of the website.

- Marketing or promotion of the website post-launch.

- Data updates beyond initial integrations.

STRATEGY

The project team will follow an agile development approach, breaking the project into iterative sprints. Requirements and stakeholder feedback will be gathered at the beginning of the project and incorporated into sprint cycles. Regular stakeholder reviews will ensure alignment and satisfaction throughout the development lifecycle. The team will use best practices in web development to ensure scalability, security, and performance.

Key Milestones:

- Requirements Gathering and Finalization

- Initial Design Prototypes

- Development and Integration of Core Features

- User Testing and Feedback Implementation

- Website Launch

DELIVERABLES

- Fully Functional Website: An interactive snow report website that meets design and functional requirements.

- API Integration: Real-time snow and weather data from reliable external sources.

- User Documentation: Comprehensive user manuals and guides for site administration.

- Testing Reports: Documentation of all testing phases, including bug fixes and performance assessments.

ACCEPTANCE CRITERIA

- Fully operational and responsive website free of critical errors.

- Accurate, real-time snow reporting across Montana ski resorts.

- Website meets usability and design expectations based on user testing feedback.

- Completion within agreed-upon timeline and budget.

CONSTRAINTS

- The project must integrate with third-party APIs for snow and weather data.

- Limited development team due to budget.

- Deployment deadline tied to the start of the ski season.

COST ESTIMATE

| Expense | Estimated Budget | Expended to Date | Estimate to Complete | Variance |
| --- | --- | --- | --- | --- |
| Internal Labor | $50,000 | $0 | $50,000 | +/- $2,000 |
| API Costs | $10,000 | $0 | $10,000 | +/- $1,000 |
| Web Hosting | $5,000 | $0 | $5,000 | +/- $500 |
| Miscellaneous | $3,000 | $0 | $3,000 | +/- $500 |
| Total | $68,000 | $0 | $68,000 | +/- $4,000 |

COST BENEFIT ANALYSIS

The benefits of this project outweigh the costs by driving user engagement, increasing resort attendance, and enhancing the experience for Montana skiers. Below is a summary:

| With Project | Without Project |
| --- | --- |
| Increased tourism revenue | No centralized resource |
| Reduced information gaps | Continued user frustration |
| User engagement through interactivity | Limited audience reach |

Net benefit is projected to be realized within the first ski season through increased resort attendance and website advertising opportunities.

Team Charter

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

03/30/25

Project Purpose:
To develop a centralized, interactive website that provides real-time snow reports for Montana ski resorts. The project aims to improve user satisfaction, enhance tourism, and support Montana’s winter sports economy through accurate, accessible data.

Team Members and Roles:

- Project Sponsor: Scott Flinders – Broken Unlimited LLC

  - Provides overall project financing.

  - Ensures alignment with organizational goals.

- Project Manager: Cameron Flinders

  - Oversees the project’s progress, coordinates team activities, and ensures timely completion of tasks.

  - Acts as the primary point of communication between stakeholders and the team.

- Development Team: Cameron Flinders

  - Responsible for designing, coding, and integrating website features.

  - Implements API connections

- Quality Assurance Team: Cameron Flinders

  - Performs rigorous testing of features and ensures the website meets acceptance criteria.

- Stakeholders:

  - Montana ski resorts, tourism boards, and outdoor enthusiasts.

Team Objectives:

- Deliver a fully functional and user-friendly website by August 1, 2025.

- Ensure real-time snow reporting accuracy through API integration and testing.

- Achieve high user satisfaction as measured by feedback post-launch.

Team Values:

- Accountability: Each team member is responsible for completing their assigned tasks on time and to quality standards.

- Innovation: Leverage best practices in web development to ensure the platform is scalable, secure, and efficient.

- Transparency: Clear updates on progress, challenges, and successes shared with stakeholders.

Operating Principles:

- Use agile methodologies

- Document all decisions, changes, and lessons learned to maintain project.

Conflict Resolution:
Conflicts within the team will be addressed promptly. Resolution methods include:

- Identifying and discussing issues

- Seeking input and finding solutions.

Resource Allocation:
The project team will have access to the following resources:

- Development tools and testing equipment for website creation.

- Dedicated time blocks to focus exclusively on project tasks.

- Third-party APIs for snow and weather data integration.

Success Metrics:

- Website launched on schedule without critical issues.

- Achieving at least 95% user satisfaction based on surveys.

- Real-time data accuracy validated during testing phases.

- Positive impact on tourism and engagement during the first ski season.

Signatures:
Project Sponsor: Scott Flinders
Project Manager: Cameron Flinders

Work Breakdown Structure

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

04/04/25

INTRODUCTION

The WBS for "Let It Snow MT" outlines the scope of work required to design, develop, and implement the website. It is a tool to facilitate effective communication among stakeholders, plan the project schedule, allocate resources, and estimate costs.

The WBS provides an outline of all activities to the third level, adhering to the 8–80 rule, where work packages represent manageable, actionable tasks.

OUTLINE VIEW

1. Let It Snow MT Website Project

1.1 Initiation

- 1.1.1 Research and feasibility analysis

- 1.1.2 Develop project charter

- 1.1.3 Submit project charter for approval

- 1.1.4 Approval of project charter

1.2 Planning

- 1.2.1 Define scope and functional requirements

- 1.2.2 Define project team

- 1.2.3 Conduct project kickoff

- 1.2.4 Develop project plan

- 1.2.5 Approve project plan

1.3 Execution

- 1.3.1 Collect and validate user requirements

- 1.3.2 Design system architecture and site layout

- 1.3.3 Develop front-end and back-end systems

- 1.3.4 Integrate snow report APIs for Montana ski hills

- 1.3.5 Conduct testing and quality assurance

- 1.3.6 Deploy website on live server

- 1.3.7 Conduct user training and onboarding

1.4 Control

- 1.4.1 Monitor project progress and risks

- 1.4.2 Conduct regular status meetings

- 1.4.3 Update project plan as required

1.5 Closeout

- 1.5.1 Conduct final system testing

- 1.5.2 Document lessons learned

- 1.5.3 Archive project files

- 1.5.4 Obtain final approval from sponsor

TREE STRUCTURE VIEW

HIERARCHICAL STRUCTURE

| Level | WBS Code | Element Name |
| --- | --- | --- |
| 1 | 1 | Let It Snow MT Website Project |
| 2 | 1.1 | Initiation |
| 3 | 1.1.1 | Research and feasibility analysis |
| 3 | 1.1.2 | Develop project charter |
| 3 | 1.1.3 | Submit project charter for approval |
| 3 | 1.1.4 | Approval of project charter |
| 2 | 1.2 | Planning |
| 3 | 1.2.1 | Define scope and functional requirements |
| 3 | 1.2.2 | Define project team |
| 3 | 1.2.3 | Conduct project kickoff meeting |
| 3 | 1.2.4 | Develop project plan |
| 3 | 1.2.5 | Approve project plan |
| 2 | 1.3 | Execution |
| 3 | 1.3.1 | Collect and validate user requirements |
| 3 | 1.3.2 | Design system architecture and layout |
| 3 | 1.3.3 | Develop front-end and back-end systems |
| 3 | 1.3.4 | Integrate snow report APIs |
| 3 | 1.3.5 | Conduct testing and QA |
| 3 | 1.3.6 | Deploy website on live server |
| 3 | 1.3.7 | Conduct user training |
| 2 | 1.4 | Control |
| 3 | 1.4.1 | Monitor project progress |
| 3 | 1.4.2 | Conduct regular status meetings |
| 3 | 1.4.3 | Update project plan as required |
| 2 | 1.5 | Closeout |
| 3 | 1.5.1 | Conduct final system testing |
| 3 | 1.5.2 | Document lessons learned |
| 3 | 1.5.3 | Archive project files |
| 3 | 1.5.4 | Obtain final approval |

WBS DICTIONARY (Example Entries)

| Level | WBS Code | Element Name | Definition |
| --- | --- | --- | --- |
| 1 | 1 | Let It Snow MT Website Project | All work required to create the website project |
| 2 | 1.1 | Initiation | Work involved to initiate the project |
| 3 | 1.1.1 | Research and feasibility analysis | Analyze project feasibility and gather research |
| 3 | 1.2.2 | Assemble project team | Identify and onboard team members |
| 3 | 1.3.4 | Integrate snow report APIs | Integrate APIs for live Montana ski hill reports |

Requirements Gathering

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

04/17/25

Requirements Gathering for Let It Snow MT Project

To ensure the Let It Snow MT project meets the documented needs and expectations of stakeholders, the following requirements have been identified. These requirements are categorized into functional, non-functional, technical, and stakeholder-based needs.

1. Functional Requirements

Functional requirements define the specific features and capabilities of the snow reporting website:

- Real-time Data Display

  - The website must provide up-to-date snow conditions for all Montana ski resorts, including snowfall in the past 24 hours, current snow depth, temperature, and resort operational status.

  - Integration with reliable APIs must ensure data updates occur at least daily.

- Interactive Map

  - Include a user-friendly map displaying snow conditions across resorts.

  - The map must allow users to zoom in and filter resorts based on location, snowfall, or other conditions.

- Customizable Filters

  - Users must be able to filter data by resort name, snowfall in the past 24 hours, snow depth, operational status, and temperature range.

  - Filters should provide results instantaneously without page reloads.

- Desktop Optimization

  - The website must be fully responsive, ensuring seamless functionality across desktop

- User-Friendly Design

  - The layout must be intuitive with a focus on simplicity and easy navigation.

  - Include clear labeling and an accessible search bar.

2. Non-Functional Requirements

Non-functional requirements address the quality and usability of the website:

- Performance

  - The website must load within 3 seconds on high-speed internet.

  - It must handle up to 1,000 concurrent users without degrading performance.

- Scalability

  - The system should support future expansion, including the ability to integrate with additional resorts or data sources.

- Security

  - Ensure secure data transmission using HTTPS.

  - Protect user data through compliance with relevant privacy laws and best practices.

- Reliability

  - Achieve 99.9% uptime during ski seasons.

  - Implement monitoring systems to detect and address API or server issues promptly.

- Accessibility

  - Ensure compliance with WCAG 2.1 standards to make the site accessible for users with disabilities.

3. Technical Requirements

Technical requirements focus on the technical specifications needed for development and deployment:

- API Integration

  - Integrate with third-party APIs providing accurate and real-time snow, weather, and resort operational data.

- Database Design

  - Develop a secure database to store a history of snow data and user logs.

- Programming Languages and Frameworks

  - Use modern development technologies, such as React for the back end and .NET application for front end

4. Stakeholder Requirements

Stakeholder requirements address the needs and wants of all parties involved in the project:

- Customers (End-Users)

  - Require an easy-to-navigate website offering quick access to snow and resort data.

  - Expect accurate and real-time updates for seamless trip planning.

- Montana Ski Resorts

  - Need a platform that promotes their operations and improves customer satisfaction.

  - Require insights on user behavior to align services with demand.

- Project Sponsor (Broken Unlimited LLC)

  - Needs the project to stay within the $68,000 budget and meet the August 1, 2025, launch deadline.

  - Expects tangible benefits like increased site traffic and advertising revenue.

- Development Team

  - Requires clear documentation, defined timelines, and access to the necessary tools and resources for project success.

5. Process Requirements

Process requirements define the project execution methods:

- Development Approach

  - Use an agile development methodology with iterative sprints, regular stakeholder reviews, and feedback incorporation.

- Testing

  - Conduct usability testing to validate the user interface and experience.

  - Perform stress testing to ensure data reliability and performance under heavy loads.

- Training and Handover

  - Ensure all documentation is delivered before deployment.

Summary:
These detailed requirements form the foundation for the Let It Snow MT project, ensuring all stakeholder needs are met and delivering a high-quality, user-friendly platform. With these requirements in place, the project team is equipped to develop a solution that successfully addresses the challenges.

Project Budget

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

05/01/25

1. Budget Overview

| Expense Category | Estimated Cost | Details |
| --- | --- | --- |
| Internal Labor | $50,000 | Developer salaries for design, development, testing, and training phases. |
| API Costs | $10,000 | Subscription fees for API integrations providing real-time snow data. |
| Web Hosting | $5,000 | Hosting costs for the website during initial deployment. |
| Miscellaneous | $3,000 | Includes tools, materials, and contingency for unforeseen expenses. |
| Total | $68,000 | Comprehensive estimate based on project proposal scope. |

2. Detailed Budget Breakdown

Labor Costs

- Design Phase: $15,000

- Development Phase: $25,000

- Testing and Training: $10,000

APIs and Infrastructure

- API Integration: $10,000

- Hosting Infrastructure: $5,000

Miscellaneous Costs

- Equipment and Software: $2,000

- Unexpected Contingencies: $1,000

3. Payment Schedule

| Payment Milestone | Amount | Payment Date | Description |
| --- | --- | --- | --- |
| Contract Signing | $20,000 | 02/28/25 | Initial payment covering labor and setup costs. |
| Prototype Approval | $15,000 | 05/01/25 | Payment upon completion of design prototypes. |
| Development Phase Completion | $20,000 | 06/15/25 | Payment upon integration of features. |
| Website Launch | $13,000 | 08/01/25 | Final payment post-launch, covering hosting fees. |

4. Notes and Assumptions

- Costs are based on industry averages and may vary depending on actual resource use.

- API fees are estimated based on current subscription models; adjustments may be necessary or removed based on use of data.

- Hosting costs include a one-year plan; long-term hosting is excluded per project scope.

- Miscellaneous funds are allocated for minor, unpredictable expenses to avoid budget overruns.

5. Risk Considerations

- API Cost Fluctuations: Monitor pricing changes and explore alternative providers if necessary.

- Resource Availability: Ensure consistent team involvement to prevent delays.

- Contingencies: Maintain a reserve to address unexpected costs.

Communication Management Plan

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

05/01/25

INTRODUCTION

The Communications Management Plan outlines how project information will be collected, created, stored, shared, and communicated among stakeholders. Effective communication ensures stakeholders are informed, aligned, and engaged, ensuring the success of the "Let It Snow MT" website development.

COMMUNICATIONS MANAGEMENT APPROACH

The approach focuses on establishing a structured communication framework, ensuring clarity, accessibility, and timeliness. Communication tools and methods are selected based on stakeholder preferences, project needs, and technological capabilities.

COMMUNICATIONS MANAGEMENT CONSTRAINTS

Key constraints include budgetary limits for communication tools, time zone differences among stakeholders, technology access, and confidentiality requirements for data.

STAKEHOLDER COMMUNICATION REQUIREMENTS

Stakeholders require updates on project progress, snow report integration status, testing outcomes, and deployment milestones. Requirements will be met through scheduled updates and detailed reports.

ROLES

Project Manager: Oversees communication processes and ensures adherence to the plan.

Developers: Report development progress and technical challenges.

Stakeholders: Provide feedback and approve key milestones.

PROJECT TEAM DIRECTORY

- Project Manager: Cameron Flinders

- Lead Developer: Cameron Flinders

- Stakeholder Representative: Not found yet

- Project Sponsor: Scott Flinders

COMMUNICATION METHODS AND TECHNOLOGIES

- Email: For formal updates.

- Video Conferencing: For monthly stakeholder meetings.

- Project Management Software: For task updates.

- Phones:  For quick team communication.

COMMUNICATIONS MATRIX

| Stakeholder Group | Communication Type | Frequency | Delivery Method | Owner |
| --- | --- | --- | --- | --- |
| Project Team | Daily Stand-ups | Daily | Video/Chat | Project Manager |
| Stakeholders | Progress Reports | Weekly | Email/Report | Project Manager |
| End Users | Announcement | Post-Deployment | Website Update | Project Manager |

COMMUNICATION FLOWCHART

GUIDELINES FOR MEETINGS

- Clearly define meeting objectives.

- Use an agenda shared in advance.

- Encourage active participation.

- Document action items and circulate minutes post-meeting.

COMMUNICATION STANDARDS

- Use clear, concise language.

- Ensure consistency in message formatting.

- Maintain confidentiality where required.

COMMUNICATION ESCALATION PROCESS

In case of unresolved issues:

- Developer/Project Manager consults stakeholder representative.

- Final decisions rest with the Project Sponsor.

Risk Register

Let It Snow MT

Broken Unlimited LLC

123 Address Ave.

Helena, MT 59601

05/01/25

1. Risk Register Overview

The purpose of this risk register is to identify, evaluate, and manage potential risks for the successful delivery of the Let It Snow MT project. Risks are categorized by their likelihood, impact, and mitigation strategies.

2. Risk Register Table

| Risk Description | Likelihood | Impact | Risk Level | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| Dependency on third-party APIs for real-time data | High | High | Critical | Conduct early API testing; maintain backup API providers. | Cameron Flinders |
| Time constraints linked to ski season deadlines | Medium | High | High | Create a detailed project timeline; regularly review milestone progress. | Cameron Flinders |
| Limited resource availability among team members | Medium | Medium | Moderate | Allocate dedicated team resources | Cameron Flinders |
| Budget overruns due to unforeseen costs | Low | High | Moderate | Maintain a reserve; monitor expenditures closely. | Scott Flinders |
| Insufficient mobile responsiveness or user issues | Low | Medium | Low | Conduct extensive user testing; gather feedback during testing. | Cameron Flinders |
| Delays in receiving stakeholder feedback | Medium | Medium | Moderate | Schedule regular stakeholder review sessions; set clear deadlines. | Cameron Flinders |
| Security vulnerabilities in website framework | Low | High | Moderate | Perform security tests; adhere to best practices in secure coding. | Cameron Flinders |

3. Risk Prioritization

Risks are prioritized based on their level (Critical, High, Moderate, Low) to ensure focus on the most significant risks.

4. Risk Monitoring and Review Plan

- Weekly Risk Review Meetings: The project members will evaluate risk statuses monthly to track changes and ensure timely responses.

- Risk Owner Accountability: Each risk has an assigned owner responsible for monitoring, mitigating, and reporting updates.

- Documentation Updates: Risk mitigations, statuses, and new risks will be continuously documented in the risk register.